## Defect Tracking Log
DEFECT TRACKING LOG
Project Name
Program Manager
Project Manager
Purpose: To ensure that the work product meets specifications for performance, defects must be tracked and fixed. These defects may arise from any Phase, but the majority will arise in the Testing Phase and must be properly captured and tracked through resolution. This form will allow documentation of test defects that must be corrected prior to project completion. Also, this form makes it easier to monitor status of the defect correction progress. This form may be used by any member of the software development team.
< Hover by the red triangle in the top left corner for more detail. Use the Instructions on the next tab to fill out fields.>
Defect No. | Date Created | Created By | Defect Description | PM Process | Lifecycle Phase | Priority | Owner | Assigned Date | Estimated Time to Fix | Status | Resolution | Resolution Date | Actual Time to Fix | Root Cause | Status | Priority | PM | Lifecycle Phase
1 | 29.12.12025 | Elmir Mujkic | 1. Open Google Chrome web browser 2. Open https://elitnutrition.ba/ 3. Navigate to a shop category 4. Use "Filter po cjeni" slider (80–200 KM). 5. There is a product with price 79.20 KM EXPECTED RESULT: Product list is refreshed and should only contain products priced between 80.00 KM and 200.00 KM inclusive. SCREENSHOTS: https://drive.google.com/file/d/10v0NcYsMulvo1NOo5MbLXNQu6Mm6qiXF/view?usp=sharing | [6 empty] | New |  |  |  |  | New
2 | 29.12.2025 | Elmir Mujkic | 1. Open Google Chrome web browser 2. Open https://elitnutrition.ba/ 3. Navigate to a shop category 4. Use "Filter po cjeni" slider (100–100 KM). 5. User is redirected to a single product detail page (“MOONS TRUCK II 510g”) whose price is 94.50 KM, which is not equal to 100.00 KM and outside the 100–100 range. EXPECTED RESULT: a) shows only products priced exactly 100.00 KM, or b) shows “no products found” if there are no products with price 100.00 KM. SCREENSHOTS: https://drive.google.com/file/d/17Qp7hUcMgE9QGF0FttyusFXSvo8iIjul/view?usp=sharing | [6 empty] | New |  |  |  |  | Under Review | High | Opportunity Assessment | Opportunity Assessment
3 | 2025-12-29 | Kerim Begic | 1. Open Google Chrome web browser 2. Open https://elitnutrition.ba/ 3. Navigate to a shop category 4. Click on some product and open product page 5.Select package, flavor and manually enter 0 for quantity 6. Click button "Dodaj u korpu" 7. Product is added to basket with quantity 1 EXPECTED RESULT : Web app should show error message like "Quantity must be >= 1" SCREENSHOTS: https://drive.google.com/file/d/1TtYVOCEqqtaH8Y_HIRjs9KPRU7tYELG_/view?usp=sharing | [6 empty] | New |  |  |  |  | In Progress | Medium | Initiating | Concept
4 | 2025-12-29 | Kerim Begic | 1. Open Google Chrome web browser 2. Open https://elitnutrition.ba/ 3.Navigate to a shop category and open any product page. ​4.Select Packaging and Flavor, and set Quantity = 1 (valid data). 5.Open Chrome DevTools → Network tab → set Network throttling to Offline. 6.Click the “Dodaj u korpu” button. 7.Mark that the product has been added to the basket EXPECTED RESULT : The web app should not show a success message while offline, it should show an error such as “No internet connection / Request failed” (or similar) SCREENSHOTS: https://drive.google.com/file/d/17ATs1pcIWeTr8sV7PuI2Od27INIy_vSX/view?usp=sharing | [6 empty] | New |  |  |  |  | Completed | Low | Planning | Requirements
5 | 2025-12-29 | Kerim Begic | 1. Open Google Chrome web browser. 2. Open https://elitnutrition.ba/. ​3. Navigate to a page where the Search field is available 4. Click in the Search input field. 5. Type a single quote character: ' and trigger search (press Enter or click the search icon). ​6. Observe the search results page (number of products shown and pagination). 7. Scroll through the results and verify whether displayed products contain ' in title/name (or are relevant to the query). 8. If pagination appears, open page 2 and repeat the verification. EXPECTED RESULT: The application should safely handle special characters used in SQL injection testing (like a single quote) and should not return unrelated it should either show a validation message (e.g., “Invalid search term”) or show “No results found” SCREENSHOTS: https://drive.google.com/file/d/1bSisKnpEeJwxGbDcmRx5pminwKV-gIY8/view?usp=sharing | [6 empty] | New | [6 empty] | Executing/Controlling | Design
6 | [16 empty] | Closing | Development
7 | [17 empty] | Testing
8 | [17 empty] | Documentation and Training
9 | [17 empty] | Deployment
10 | [17 empty] | Post-Deployment
11
12
13
14
15
16
17
18
Note on E10: ====== ID#AAAAn_rmfi0 Julie Arnold (2023-01-09 19:26:29) Choose from the drop down box.
Note on F10: ====== ID#AAAAn_rmfiw John Casey (2023-01-09 19:26:29) Choose from the drop down box.
Note on G10: ====== ID#AAAAn_rmfio Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list
Note on K10: ====== ID#AAAAn_rmfis Julie Arnold (2023-01-09 19:26:29) Choose from the drop down list.